## 8846 ADJUSTMENT
Target Plan
[6 empty] | Classification |  | YEAR 2023 |  |  | Total Number of Personnel for Automation Project: 1
February (as of Feb. 15)
[8 empty] | Target | Actual
[6 empty] | Sir Jogie's Request |  | 100% | 10%
*Date Started: February 01, 2023 (Tue-Fri)
[6 empty] | Activity | % Completed | % Breakdown | # of Parameters | Completed | Pending
[6 empty] | User Interface | 15 | 15 | 15 | 15 | 0
[6 empty] | Codes Preparation | 23.3333 | 50 | 15 | 7 | 8
[6 empty] | Debugging/Testing | 6.6667 | 25 | 15 | 4 | 11
[6 empty] | Implementation | 0 | 10 | 15 | 0 | 15 | Jan 30 to Feb 24
[6 empty] | Completed | 45 | 100 | 15 | 26 | 34
[6 empty] | Pending | 55
[7 empty] | Month | Day | Year
[6 empty] | Date | Feb. | 1 | 2023
[6 empty] | Date | Feb. | 15 | 2023
TARGET | TOTAL | Pending | Total Codes Completed | Completion Rate
#REF!
8845A/8846A | for 8845A
2 | 100% | 55 | 23.3333 | 45
|  |  | Covered Date: | Feb. 1, 2023 to Feb. 15, 2023
Automation Project Update Line-up
[5 empty] | ✔ | Datasheet Templates Update
Software Validation
C - Completed | [5 empty] | Calibration Procedure Update
H - On Hold | [5 empty] | Method Validation of Procedure
T - On Track